# SCHOOL EVENT or GALA Maximization Hints

1. 	Approach Influential People & Businesses involved with the school and ask them to setup promotions, sponsor entertainment & fundraising equipment or provide some food beverages & prizes for stalls, raffles & entertainment - CONTRA Advertising & assistance on stalls for School fees.

2. 	Organise Schedule Action Plan with delegated responsibilities for Teachers & Parents with suitable skills - setting out stall & event areas, traffic control, MC, Signage for toilets & stalls, making artwork, sweets, produce to sell collection.

3. 	Form Schedule of Events Booklet with advertising outlining timetable, the where & how to find everything and everyone - eg Lost Children Centre

4.	Form a Site Plan with Access, Power, Toilets, Water, People Flow, Area Plan Fire & Ambulance Safety Access with times for Set-up & checklist materials

5. 	Assign responsibilities for Stall Supervision / Admin./ Refreshments / Toilets / Fire safety / Rubbish / Security / Lost People / PA Station & Firstaid

6.	 Book agreed entertainment & fundraising equipment, catering to all ages.

7. 	Power - have an electrician workout what you need, leads, generator etc.

8. 	Market Event -Advertising (sponsorship) large signs, newspapers, radio & 	Presell discount tickets, distribute newsletters to a action timetable

9. 	Promote & Pre-sell Tickets, centralised ticketing & BANK with Eftpos Facilities  this means NO $$$ (money) at stalls or rides and money in hand prior to day

10.	 Setup as much as possible the Day / Night before and appoint Security .

11. 	Checklist duties with rosters and times, if something isn’t working change it!

12. 	Setup communications centre -PA System,  Music & MC

13. 	Continual Cleanup / Countup whilst in progress to save a huge job at the end.

FINALE

14. 	Debrief to work out how to tuneup the system for next-time with drinks !!

15. 	Have an after event function - Announce & reward those who deserve it !

16. 	Write letters of recognition and certificates to all who helped, especially sponsors, local businesses and put photos in local rag showing good times.

17.	Allow for wet weather -Plan B or allow for everything to be under cover

Compliments  from.........

ROCKUP Directors   - Geoff & Lynne Pearson

0800 ROCKUP (0800 762 587)     www.rockup.co.nz   email: rockup@ihug.co.nz